## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Create Login Page | 1 | 0
Login | Create credentials data base | 1
Login | Implement credentials validation process | 2
Register | Create register page | 1
Register | Implement register process | 2
Create home page | Create "Home Page" | 1
Create home page | Implement "Home Page" functionality | 3
Create Inventory | Create "Inventory Page" | 1
Create Inventory | Add user info at screen | 1
Create Inventory | Implement add button for Raw Material | 2
Create Inventory | Implement edit button for Raw Material | 2
Create Inventory | Implement order material button for Raw Material | 2
Create Inventory | Implement remove button for Raw Material | 2
Create Inventory | Implement Product recipe functionality | 3
Create Inventory | Implement add button for Product | 2
Create Inventory | Implement edit button for Product | 2
Create Inventory | Implement order material button for Product | 2
Create Inventory | Implement remove button for Product | 2
Create Orders | Create Orders page | 1
Create Orders | Implement Open Orders list view | 3
Create Orders | Implement Closed Orders list view | 3
Create Orders | Create orders data base | 3
| Estimate Totals | 42 | 0 | 0 | 0 | 0