## Sprint1
Related User Story |  | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Jason | Create Login Page | 1 | 1 | 0 | 0 | 0
Login | Jason | Create credentials data base | 5 | 4 | 1 | 0 | 0
Login | Jason | Implement credentials validation process | 3 | 2 | 1 | 0 | 0
Register | JH | Create register page | 1 | 1 | 0 | 0 | 0
Register | JH | Implement register process | 6 | 6 | 3 | 0 | 0
Create home page | JE | Create "Home Page" | 1 | 1 | 0 | 0 | 0
Create home page | JE | Implement "Home Page" functionality | 3 | 3 | 3 | 0 | 0
Create Inventory | Vitor | Create "Inventory Page" | 1 | 0 | 0 | 0 | 0
Create Inventory | Vitor | Add user info at screen | 1 | 1 | 1 | 1 | 0
Create Inventory | Vitor | Implement add button for Raw Material | 3 | 2 | 1 | 0 | 0
Create Inventory | Vitor | Implement edit button for Raw Material | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor | Implement order material button for Raw Material | 2 | 2 | 2 | 2 | 0
Create Inventory | Vitor | Implement remove button for Raw Material | 3 | 2 | 1 | 0 | 0
Create Inventory | Vitor | Implement Product recipe functionality | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor | Implement add button for Product | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor | Implement edit button for Product | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor | Implement order material button for Product | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor | Implement remove button for Product | 3 | 2 | 1 | 1 | 0
Create Orders | JE | Create Orders page | 1 | 1 | 0 | 0 | 0
Create Orders | JE | Implement functionality for orders | 2 | 2 | 0 | 0 | 0
Create Orders | JE | Testing for orders functionality | 2 | 2 | 0 | 0 | 0
Create Orders | JE | Implement Open Orders list view | 2 | 2 | 2 | 2 | 0
Create Orders | JE | Implement Closed Orders list view | 2 | 2 | 2 | 2 | 0
Create Orders | JE | Create orders data base | 3 | 3 | 3 | 3 | 0
|  | Estimate Totals | 60 | 49 | 26 | 16 | 0