## Sprint 2
Related User Story | Assigned To | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Vitor | Create the Server implementation of the Employee Creds | 8 | 7 | 5 | 0 | 0
Inventory | Jason | Create the Server implementation of the Product Inventory | 7 | 6 | 5 | 0 | 0
Inventory | Jason | Create the Server implementation of the Component Inventory | 7 | 6 | 5 | 0 | 0
Order | Jason | Create the Server implementation of the Order Inventory | 8 | 6 | 5 | 0 | 0
Inventory | Jason | Create WarehouseInventory Façade | 2 | 2 | 2 | 2 | 2
Login | Jason | Migrate the Login ViewModel from Local Impl to Server Impl | 5 | 5 | 5 | 0 | 0
Inventory | Jason | Migrate the Inventory ViewModels from Local Impl to Server Impl | 5 | 5 | 5 | 0 | 0
Inventory | Jason | Create DemoData for the Server Impl | 1 | 1 | 1 | 1 | 0
Order | Jason | Migrate the Order ViewModel from Local Impl to Server Impl | 5 | 5 | 5 | 0 | 0
Login | Vitor | Migrate Credential Manager from Local Impl to Server Impl | 2 | 0 | 0 | 0 | 0
Admin | Vitor | Create the Admin View | 1 | 0 | 0 | 0 | 0
Admin | Vitor | Implement Functionality in the Admin page | 4 | 4 | 0 | 0 | 0
Login | JH | Implement the Functionality to "hold" the login employee type | 3 | 3 | 3 | 3 | 0
Inventory | JE | Implement Functionality to hide buttons based on the employee's role | 1 | 1 | 1 | 1 | 0
Order | JE | Implement Functionality to hide buttons based on the employee's role | 1 | 1 | 1 | 1 | 0
Admin | JE | Implement Functionality to hide buttons based on the employee's role | 1 | 1 | 1 | 1 | 0
Inventory | JH | Implement the Functionality to search for a specific product | 3 | 3 | 3 | 3 | 0
Inventory | JE | Implement the Functionality to search for a specific component | 2 | 2 | 2 | 2 | 0
Inventory | JE | Implement the ability to export recipes | 3 | 3 | 3 | 3 | 0
Inventory | JE | Implement the ability to import recipes | 3 | 3 | 3 | 3 | 0
Home |  | Implement a "Loading" text whenever the GUI is fetching information from the server | 2 | 2 | 2 | 2 | 2
Home |  | Change ComponentAnalytics to use the Server Impl | 2 | 2 | 2 | 0 | 0
Home | JE | Change ProductAnalytics to use the Server Impl | 2 | 2 | 2 | 0 | 0
Home |  | Change OrderAnalytics to use the Server Impl | 2 | 2 | 2 | 0 | 0
Home | JE | Improve usability through consistent sidebar navigation | 2 | 2 | 0 | 0 | 0
Home | Vitor | Implement employee summary | 3 | 3 | 3 | 3 | 0
Inventory | JH | Improve usability through changing confirmation dialogs | 3 | 2 | 0 | 0 | 0
Inventory | JH | Fix producing a product to specify an amount | 3 | 3 | 3 | 0 | 0
Inventory | JH | Adjust Component Add/Edit to only allow valid inputs (No numbers on costs etc) | 3 | 3 | 2 | 0 | 0
Inventory | JH | Adjust Product Add/Edit to only allow valid inputs (No numbers on costs etc) | 3 | 3 | 2 | 0 | 0
Server |  | Implement Tests for the Components Server Side | 3 | 3 | 3 | 3 | 3
Server |  | Implement Tests for the Products Server Side | 3 | 3 | 3 | 3 | 3
Server |  | Implement Tests for the Orders Server Side | 3 | 3 | 3 | 3 | 3
|  | Estimate Totals | 80 | 72 | 63 | 22 | 4
Bugs from last sprint
Require server implementation

## Sprint1
Related User Story |  | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Jason | Create Login Page | 4 | 3 | 2 | 1 | 0
Login | Jason | Create credentials data base | 7 | 5 | 2 | 0 | 0
Login | Jason | Implement credentials validation process | 2 | 2 | 1 | 0 | 0
Register | JH | Create register page | 3 | 2 | 1 | 0 | 0
Register | JH | Implement register process | 4 | 4 | 2 | 1 | 0
Create home page | JE | Create "Home Page" | 6 | 7 | 5 | 2 | 0
Create home page | JE | Implement "Home Page" functionality | 4 | 3 | 3 | 2 | 0
Create Inventory | Vitor/Jason | Create "Inventory Page" | 25 | 20 | 12 | 7 | 0
Create Inventory | Vitor/Jason | Add user info at screen | 1 | 1 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement add button for Raw Material | 3 | 2 | 1 | 0 | 0
Create Inventory | Vitor/Jason | Implement edit button for Raw Material | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement order material button for Raw Material | 2 | 2 | 2 | 2 | 0
Create Inventory | Vitor/Jason | Implement remove button for Raw Material | 3 | 2 | 1 | 0 | 0
Create Inventory | Vitor/Jason | Implement Product recipe functionality | 5 | 3 | 2 | 1 | 0
Create Inventory | Vitor/Jason | Implement add button for Product | 5 | 3 | 2 | 1 | 0
Create Inventory | Vitor/Jason | Implement edit button for Product | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement order material button for Product | 2 | 2 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement remove button for Product | 2 | 2 | 1 | 1 | 0
Create Orders | JE | Create Orders page | 2 | 2 | 1 | 1 | 0
Create Orders | JE | Implement functionality for orders | 5 | 3 | 2 | 1 | 0
Create Orders | JE | Testing for orders functionality | 2 | 2 | 0 | 0 | 0
Create Orders | JE | Implement Open Orders list view | 2 | 2 | 2 | 2 | 0
Create Orders | JE | Implement Closed Orders list view | 2 | 2 | 2 | 2 | 0
Create Orders | JE | Create orders data base | 3 | 3 | 3 | 3 | 0
|  | Estimate Totals | 100 | 81 | 51 | 31 | 0