## Sprint 2
Related User Story | Assigned To | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Vitor | Create the Server implementation of the Employee Creds | 0 | 0 | 0 | 0 | 0
Inventory |  | Create the Server implementation of the Product Inventory | 0 | 0 | 0 | 0 | 0
Inventory |  | Create the Server implementation of the Component Inventory | 0 | 0 | 0 | 0 | 0
Order |  | Create the Server implementation of the Order Inventory | 0 | 0 | 0 | 0 | 0
Login | Vitor | Migrate the Login ViewModel from Local Impl to Server Impl | 0 | 0 | 0 | 0 | 0
Inventory |  | Migrate the Inventory ViewModels from Local Impl to Server Impl | 0 | 0 | 0 | 0 | 0
Order |  | Migrate the Order ViewModel from Local Impl to Server Impl | 0 | 0 | 0 | 0 | 0
Admin | Vitor | Create the Admin View | 0 | 0 | 0 | 0 | 0
Admin | Vitor | Implement Functionality in the Admin page | 0 | 0 | 0 | 0 | 0
Login | Vitor | Implement the Functionality to "hold" the login employee type | 0 | 0 | 0 | 0 | 0
Home |  | Implement the Functionality to display the current employee's information | 0 | 0 | 0 | 0 | 0
Inventory |  | Implement Functionality to hide buttons based on the employee's role | 0 | 0 | 0 | 0 | 0
Order |  | Implement Functionality to hide buttons based on the employee's role | 0 | 0 | 0 | 0 | 0
Admin |  | Implement Functionality to hide buttons based on the employee's role | 0 | 0 | 0 | 0 | 0
Inventory |  | Implement the Functionality to search for a specific product | 0 | 0 | 0 | 0 | 0
Inventory |  | Implement the Functionality to search for a specific component | 0 | 0 | 0 | 0 | 0
Inventory |  | Implement the ability to export recipes | 0 | 0 | 0 | 0 | 0
Inventory |  | Implement the ability to import recipes | 0 | 0 | 0 | 0 | 0
Home |  | Change ComponentAnalytics to use the Server Impl | 0 | 0 | 0 | 0 | 0
Home |  | Change ProductAnalytics to use the Server Impl | 0 | 0 | 0 | 0 | 0
Home |  | Change OrderAnalytics to use the Server Impl | 0 | 0 | 0 | 0 | 0
Inventory |  | Add shelf Life to Component | 0 | 0 | 0 | 0 | 0
Inventory |  | Add shelf Life to Product | 0 | 0 | 0 | 0 | 0
Home |  | Implement Component shelf life analytics to ComponentAnalytics | 0 | 0 | 0 | 0 | 0
Home |  | Implement product shelf life analytics to ProductAnalytics | 0 | 0 | 0 | 0 | 0
Admin |  | Add Customizeable Alerts Settings Page | 0 | 0 | 0 | 0 | 0
Home |  | Implement the ability to receive notifications about low stock levels on login | 0 | 0 | 0 | 0 | 0
Inventory |  | Add "Minimum Stock" to Component for Automated Reordering | 0 | 0 | 0 | 0 | 0
Inventory |  | Add Ability to enabled/disable automated reordering for specific components | 0 | 0 | 0 | 0 | 0
Orders |  | Add Data Needed/Order Date to Orders | 0 | 0 | 0 | 0 | 0
Support |  | Add Ability to mimic progression of days for demo purposes | 0 | 0 | 0 | 0 | 0
|  | Estimate Totals | 0 | 0 | 0 | 0 | 0

## Sprint1
Related User Story |  | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Jason | Create Login Page | 4 | 3 | 2 | 1 | 0
Login | Jason | Create credentials data base | 7 | 5 | 2 | 0 | 0
Login | Jason | Implement credentials validation process | 2 | 2 | 1 | 0 | 0
Register | JH | Create register page | 3 | 2 | 1 | 0 | 0
Register | JH | Implement register process | 4 | 4 | 2 | 1 | 0
Create home page | JE | Create "Home Page" | 6 | 7 | 5 | 2 | 0
Create home page | JE | Implement "Home Page" functionality | 4 | 3 | 3 | 2 | 0
Create Inventory | Vitor/Jason | Create "Inventory Page" | 25 | 20 | 12 | 7 | 0
Create Inventory | Vitor/Jason | Add user info at screen | 1 | 1 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement add button for Raw Material | 3 | 2 | 1 | 0 | 0
Create Inventory | Vitor/Jason | Implement edit button for Raw Material | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement order material button for Raw Material | 2 | 2 | 2 | 2 | 0
Create Inventory | Vitor/Jason | Implement remove button for Raw Material | 3 | 2 | 1 | 0 | 0
Create Inventory | Vitor/Jason | Implement Product recipe functionality | 5 | 3 | 2 | 1 | 0
Create Inventory | Vitor/Jason | Implement add button for Product | 5 | 3 | 2 | 1 | 0
Create Inventory | Vitor/Jason | Implement edit button for Product | 3 | 2 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement order material button for Product | 2 | 2 | 1 | 1 | 0
Create Inventory | Vitor/Jason | Implement remove button for Product | 2 | 2 | 1 | 1 | 0
Create Orders | JE | Create Orders page | 2 | 2 | 1 | 1 | 0
Create Orders | JE | Implement functionality for orders | 5 | 3 | 2 | 1 | 0
Create Orders | JE | Testing for orders functionality | 2 | 2 | 0 | 0 | 0
Create Orders | JE | Implement Open Orders list view | 2 | 2 | 2 | 2 | 0
Create Orders | JE | Implement Closed Orders list view | 2 | 2 | 2 | 2 | 0
Create Orders | JE | Create orders data base | 3 | 3 | 3 | 3 | 0
|  | Estimate Totals | 100 | 81 | 51 | 31 | 0